## ProjectTeam
Name | GitHub Alias
Sarah Mele | meles1
Yannis Portmann | porty1
Luca Brito Ramos | ramol1
Shpend Vladi | vlads1
Manuel Pfister | pfism11

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
0 | Prototype | Modifying Prototype | high | 0h | 2h | 2h | done
1 | Login | Login and Homescreen of the Application for the Doctor | high | 0h | 25h | 41h | done
2 | Patient | Searching for a Patient. Record a new Patient. Edit Patient Data. | high | 55h | 55h | 27h | progress
3 | Case | Record a new case. Add diagnosis. Add Treatment. Edit Case. | high | 75h | 58h | 65h | progress
4 | Message | Send and receive messages between Doctor and Patient | low | 20h | 2h | 2h | waiting
5 | State Pattern | State Pattern for Sprint 2 | high | 0h | 8h | 8h | done

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort (h) Plan Original | Effort (h) Plan Updated | Effort Actual | Status
0 | 1 | Prototypes | Modify Prototypes | Prototype | Mele | Portmann | high | 0 | 2 | 2 | done
1 | 1 | GUI | Application GUI needs to be designed and prepared for further steps | UI | Mele | Vladi | high | 3 | 9 | 9 | done
1.1 | 1 | Login | Data model for doctor login | Database | Pfister | Mele | high | 2 | 6 | 6 | done
1.2 | 1 | Login | User Interface for Login | UI | Mele | Vladi | high | 4 | 6 | 6 | done
1.3 | 2 | Login | Login functionality | Controller | Pfister | Mele | normal | 5 | 6 | 6 | done
1.4 | 2 | Home | User Interface for Home | UI | Mele | Portmann | high | 0 | 9 | 9 | done
1.5 | 2 | Home | Functionality Calendar | Controller | Mele | Portmann | high | 0 | 5 | 5 | done
2.1 | 1 | Patient | Data model for patient record | Database | Vladi | Portmann | normal | 3 | 4 | 4 | done
2.2 | 2 | Patient | User Interface needs to be designed | UI | Portmann | Vladi | normal | 7 | 7 | 7 | done
2.3 | 2 | Patient | edit Data, save Data | Controller | Portmann | Vladi | normal | 15 | 16 | 16 | progress
3.1 | 1 | Case | Data model for Case, Diagnosis, Treatment and Medication | Database | Vadi / Ramos | Portmann | high | 20 | 7 | 7 | done
3.2 | 2 | Case | User Interface | UI | Vladi / Ramos | Portmann | normal | 30 | 25 | 25 | done
3.3 | 2 | Case | Functionality for new Case, new Diagnosis, new Treatment, edit Treatment, delete Treatment, edit Diagnosis, new Medication, edit Medication and Delete Medication | Controller | Mele, Portmann, Vladi, Ramos | Mele / Portmann | high | 44 | 38 | 33 | progress
4.1 | 3 | Message | Data model for Message | Database | Ramos | Mele | low | 5 | 1 | 1 | done
4.2 | 3 | Message | User Interface | UI | Mele | Mele | low | 5 | 1 | 1 | done
4.3 | 3 | Message | create/send/receive Message, delete Message | Controller | Ramos | Mele | low | 7 | 0 | 0 | waiting
5.1 | 2 | State Pattern | high | View with Logic | Portmann, Mele | Mele | high | 0 | 8 | 8 | done
[7 empty] | Total | 150 | 150 | 145

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-12-02 | 30 | 0
2 | 2015-12-17 | 12 | 2
3 | 2016-01-14 | 5 | 0