## ProjectTeam
Name | GitHub Alias
Sarah Mele | meles1
Yannis Portmann | porty1
Luca Brito Ramos | ramol1
Shpend Vladi | vlads1
Manuel Pfister

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Patient | Record a new Patient. Edit Patient Data. | high | 55h |  | 10 | waiting
2 | Message | Send and receive messages between Doctor and Patient | low | 20h |  | 1 | waiting
3 | Case | Record a new case. Add diagnosis. Add Treatment. Edit Case. | high | 75h |  | 11 | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort (h) Plan Original | Effort (h) Plan Updated | Effort Actual | Status
1 | 1 | GUI | Application GUI needs to be designed and prepared for further steps | UI | Mele | Vladi | high | 3 | 3 | 3 | waiting
1.1 | 1 | Login | Data model for doctor login | Database | Pfister | Mele | high | 2 | 2 | 2 | waiting
1.2 | 1 | Login | User Interface for Login | UI | Pfister |  | high | 4 | 3 | 3 | waiting
1.3 |  | Login | Login functionality | Controller | Pfister |  |  | 5 |  | 0 | waiting
2.1 | 1 | Patient | Data model for patient record | Database | Vladi | Portmann | high | 3 | 2 | 2 | waiting
2.2 |  | Patient | User Interface needs to be designed | UI | Vladi |  |  | 7 |  | 0 | waiting
2.3 |  | Patient | create new Patient, edit Data, save Data | Controller | Vladi |  |  | 15 |  | 0 | waiting
3.1 | 1 | Message | Data model for Message | Database | Ramos |  |  | 5 |  | 1 | waiting
3.2 |  | Message | User Interface | UI | Mele |  |  | 5 |  | 0 | waiting
3.3 |  | Message | create/send/receive Message, delete Message | Controller | Ramos |  |  | 7 |  | 0 | waiting
4.1 | 1 | Case | Data model for Case, Diagnosis, Treatment and Medication | Database | Portmann | Ramos | high | 20 | 10 | 5 | waiting
4.2 | 1 | Case | User Interface | UI | Portmann |  |  | 30 |  | 6 | waiting
4.3 |  | Case | Functionality for new Case, new Diagnosis, new Treatment, edit Treatment, delete Treatment, edit Diagnosis, new Medication, edit Medication and Delete Medication | Controller | Mele Portmann |  |  | 44 |  | 0 | waiting
22

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-11-19 | 30 | 9
2 | 2015-11-19 | 70 | 70
3 | 2015-11-19 | 50 | 50