## ProjectTeam
Name | GitHub Alias
Sarah Mele | meles1
Yannis Portmann | porty1
Luca Brito Ramos | ramol1
Shpend Vladi | vlads1

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Patient | Record a new Patient. Edit Patient Data. | high | 35h | 35h | 0h | waiting
2 | Message | Send and receive messages between Doctor and Patient | low | 20h | 20h | 0h | waiting
3 | Case | Record a new case. Add diagnosis. Add Treatment. Edit Case. | high | 65h | 65h | 0h | waiting
waiting
work in progress
done

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Patient | Data model for patient record needs to be created based on standard sql. | Database | Martin | Hans | high | 2 | 2 | 0 | waiting
1.2 | 1 | Patient | Data model for doctor login record needs to be created based on standard sql. | Database | Hans | Jennifer | high | 8 | 8 | 0 | waiting
1.3 | 1 | Patient | Create class Patient |  | Martin | Tom | high | 16 | 16 | 0 | done
2.1 | 1 |  |  |  | Tom | Martin | low | 4 | 4 | 0 | cancelled
2.2 | 2 |  |  |  | Jennifer | Martin | high | 8 | 8 | 0 | work in progress
|  |  |  | UI, Controller | [6 empty] | waiting
|  |  |  | All |  |  | low |  |  |  | work in progress
|  |  |  | Database |  |  | high |  |  |  | done
|  |  |  | Main Window |  |  | medium |  |  |  | cancelled
work in progress

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-11-19 | 24 | 24
2 | 2015-11-19 | 56 | 56
3 | 2015-11-19 | 40 | 40